## Project Planner
Project Plan |  |  | Period Highlight: | 29 |  |  | Plan Duration
ACTIVITY | PLAN START | PLAN DURATION | PERCENT COMPLETE | November |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May
|  |  |  | 11th - 17th | 18th | 25th | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 4th | 11th | 18th | 25th
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Research
Initial Research | 1 | 1 | 100%
Loot box Research | 1 | 2 | 100%
Gambling Research | 1 | 2 | 100%
Project Planning | 1 | 4 | 90%
Background Reading | 1 | 25 | 65%
Assignments
Create Project Plan | 1 | 4 | 90%
Create Design Presentation | 5 | 5 | 0%
Create draft report for review | 10 | 10 | 0%
Create Exhibition Demonstration | 20 | 9 | 0%
Write Dissertation | 4 | 22 | 0%
Design
Create 3D Models | 4 | 2 | 0%
Create Loot Box Simulator | 4 | 4 | 0%
Finalise rewards system | 4 | 5 | 25%
Create Horse racing mini-game | 7 | 4 | 0%
Testing
Testing phase 1 - just lootboxes | 8 | 7 | 0%
Testing phase 2 - with added horse racing | 16 | 7 | 0%